## Summary
Hermes Desktop / SPS Agent Feature Status | Hermes Desktop / SPS Agent Feature Status | Hermes Desktop / SPS Agent Feature Status | Hermes Desktop / SPS Agent Feature Status | Hermes Desktop / SPS Agent Feature Status | Hermes Desktop / SPS Agent Feature Status
Generated 2026-06-22T01:28:40.502Z from current checkout source evidence. | Generated 2026-06-22T01:28:40.502Z from current checkout source evidence. | Generated 2026-06-22T01:28:40.502Z from current checkout source evidence. | Generated 2026-06-22T01:28:40.502Z from current checkout source evidence. | Generated 2026-06-22T01:28:40.502Z from current checkout source evidence. | Generated 2026-06-22T01:28:40.502Z from current checkout source evidence.
Area | Features | Implemented | Covered by existing automated evidence | Manual QA pending | P0 count
App lifecycle | 6 | 6 | 6 | 5 | 4
Connection | 1 | 1 | 1 | 1 | 1
Admin Control Center | 9 | 9 | 9 | 5 | 1
Workspace shell | 5 | 5 | 5 | 3 | 3
Docs and wiki | 8 | 8 | 8 | 3 | 3
Storage | 5 | 5 | 5 | 1 | 3
Media and capture | 3 | 3 | 3 | 1 | 0
Obsidian | 2 | 2 | 2 | 1 | 0
Review and safety | 2 | 2 | 2 | 1 | 1
Research | 10 | 10 | 10 | 4 | 1
Content | 2 | 2 | 2 | 2 | 0
Work management | 6 | 6 | 6 | 4 | 1
Assistant and chat | 4 | 4 | 4 | 2 | 3
Personalization | 2 | 2 | 2 | 1 | 0
Learning | 2 | 2 | 2 | 0 | 0
Journal and health | 2 | 2 | 2 | 2 | 0
Gateway and backend | 5 | 5 | 5 | 1 | 2
Security | 3 | 3 | 3 | 2 | 3

## Feature Status
ID | Area | Feature | User Story | Expected Behaviour | Source Evidence | Code Status | Current Test Status | Priority | Manual Test Plan | Last Tested | Observed Errors | Fix Status | Retest Evidence | Notes
HF-001 | App lifecycle | Startup routing and timeout diagnostics | As a user launching SPS Agent, I want startup checks to route me to the right screen or recovery action so I am not trapped on a blank loader. | The app checks connection settings, onboarding state, local install, remote health, or SSH tunnel with bounded timeouts; timeout cards offer retry, install, local switch, and copy diagnostics. | src/renderer/src/App.tsx:31-404 | Implemented | PASS: App.test.tsx lifecycle coverage; manual startup scenarios pending | P0 | Launch with local, missing install, missing key, remote failure, SSH timeout, and verify diagnostic controls. | 2026-06-22 |  | Not needed | npx vitest run src/renderer/src/App.test.tsx: included in 44-file renderer slice, 324 tests passed.
HF-002 | App lifecycle | Welcome and install recovery | As a first-time or broken-install user, I want to start installation, recheck, or switch to local mode so I can recover without editing files. | Welcome receives install errors and connection mode; Start install opens installer, Recheck reruns startup, and Switch local updates connection config. | src/renderer/src/App.tsx:347-428 | Implemented | PASS: App.test.tsx route coverage; manual forced-state QA pending | P0 | Force welcome state, trigger each action, and verify screen/state changes. | 2026-06-22 |  | Not needed | npx vitest run src/renderer/src/App.test.tsx: included in 44-file renderer slice, 324 tests passed.
HF-003 | App lifecycle | Hermes installer flow | As a user without Hermes Agent installed, I want the desktop app to run and display the official install flow so the agent becomes usable. | Installing screen starts installation, streams progress, handles completion, failure, and cancel back to Welcome. | src/renderer/src/screens/Install/Install.tsx | Implemented | PASS: installer unit tests; manual throwaway-HERMES_HOME QA pending | P0 | Run dev:fresh, start install, verify progress, cancel, success, and failed-install messaging. | 2026-06-22 |  | Not needed | npx vitest run tests/installer-*.test.ts: included in backend slice; installer tests passed.
HF-004 | App lifecycle | Provider setup gate | As a user with Hermes installed but no API key, I want setup to collect provider credentials before entering the workspace. | Startup routes to Setup when checkInstall reports installed but hasApiKey false; setup completion routes through onboarding state. | src/renderer/src/App.tsx:298-458 | Implemented | PASS: App/provider install-gate tests; manual credential QA pending | P0 | Launch with no key, save provider key, verify onboarding/workspace transition and key redaction. | 2026-06-22 |  | Not needed | npx vitest run src/renderer/src/App.test.tsx tests/install-gate-providers.test.ts tests/providers.test.ts: passed in focused slices.
HF-005 | App lifecycle | First-run onboarding | As a new user, I want guided onboarding before the workspace so I can configure the essentials. | Onboarding is shown until getOnboardingCompleted is true; finish persists completion; configure buttons deep-link into admin tabs. | src/renderer/src/App.tsx:283-475 | Implemented | PASS: verify-firstrun-seed covers seeded checklist entry | P1 | Reset onboarding flag, complete onboarding, use provider/model deep links, relaunch. | 2026-06-22 | First-run seed verifier initially expected stale .ob-step selectors while the app renders .ob-step-card. | Fixed harness | node scripts/verify-firstrun-seed.mjs: checklist renders, has 3 steps, dismiss hides it. | The separate pre-workspace Onboarding screen still needs a manual reset-and-complete QA pass.
HF-006 | App lifecycle | Soft verify-install warning | As a user whose local install exists but deep verification fails, I want a warning instead of being bounced out of the app. | verifyInstall runs in background for non-remote modes; failure shows a dismissible warning with reinstall path. | src/renderer/src/App.tsx:319-338 | Implemented | PASS: App.test.tsx warning route coverage; manual warning UI QA pending | P1 | Mock verifyInstall false and confirm warning, dismiss, and reinstall actions. | 2026-06-22 |  | Not needed | npx vitest run src/renderer/src/App.test.tsx: included in 44-file renderer slice, 324 tests passed.
HF-007 | Connection | Local, remote, and SSH modes | As a user, I want to connect to a local Hermes gateway, a remote URL, or an SSH tunnel so I can use the app across environments. | Connection config decides startup behavior; remote health is tested, SSH tunnel is started, and remote-only admin screens show restrictions. | src/main/ipc/config.ts:258-360 | Implemented | PASS: connection/remote/SSH tests; manual live connection QA pending | P0 | Exercise local, remote valid/invalid, SSH valid/invalid, and remote-only admin restrictions. | 2026-06-22 | Sandbox run blocked loopback listeners with listen EPERM on 127.0.0.1. | Environment rerun | Escalated rerun of tests/connection-config-security.test.ts, tests/model-discovery.test.ts, and tests/chat-client-streaming.test.ts passed: 20 tests.
HF-008 | Admin Control Center | Admin overlay keyboard and deep links | As a workspace user, I want settings to open from gear, Command-comma, or deep links without leaving SPS. | Admin overlay traps focus, Escape closes it, explicit views normalize through openSettings, and last/default view is respected. | src/renderer/src/App.tsx:86-196 | Implemented | PASS: verify-admin-overlay; partial verify-agentic-ui preferences deep-link | P1 | Open via gear, status chips, banners, Command-comma, Escape, and keyboard tab traversal. | 2026-06-22 | No product error in admin overlay smoke; verify-agentic-ui used legacy settings alias and opened the wrong section before harness fix. | Fixed harness | node scripts/verify-admin-overlay.mjs: VERIFY_DONE, 5 screenshots; node scripts/verify-agentic-ui.mjs: 11/11 passed. | Harness now deep-links to hermes:open-settings view preferences instead of the legacy settings alias.
HF-009 | Admin Control Center | Overview dashboard | As an operator, I want a Control Center overview so I can see setup and workspace health quickly. | Overview is the default admin tab and can navigate to grouped admin sections. | src/renderer/src/screens/Layout/Layout.tsx:31-60,322-328 | Implemented | PASS: ControlCenterOverview component test | P1 | Open Overview, verify cards/links navigate to the correct sections. | 2026-06-22 |  | Not needed | npx vitest run src/renderer/src/screens/Layout/ControlCenterOverview.test.tsx: included in 44-file renderer slice, 324 tests passed.
HF-010 | Admin Control Center | AI Setup / Providers | As a user, I want to manage provider credentials, OAuth, tests, and Hermes Agent refresh status in one AI setup surface. | Providers is shown in AI Setup unless remote-only; it supports provider state, credential pools, OAuth status, tests, and updater routine history. | src/renderer/src/screens/Providers/Providers.tsx | Implemented | PASS: Providers.test.tsx and provider backend tests; manual credential QA pending | P0 | Add/remove/test API-key provider, sign in/out OAuth provider, inspect update routine controls. | 2026-06-22 |  | Not needed | npx vitest run src/renderer/src/screens/Providers/Providers.test.tsx plus provider/model backend tests: passed in focused slices.
HF-011 | Admin Control Center | Models catalog | As a user, I want to view and configure available models so chat and assistant flows use the right backend. | Models tab lazy-mounts in admin, lists provider models, and respects visibility. | src/renderer/src/screens/Models/Models.tsx | Implemented | PASS: Models.test.tsx and model-discovery tests | P1 | Open Models, switch providers, verify discovered/default model behavior. | 2026-06-22 | Sandbox run blocked model-discovery loopback listeners with listen EPERM on 127.0.0.1. | Environment rerun | npx vitest run src/renderer/src/screens/Models/Models.test.tsx passed; escalated model-discovery rerun passed with affected loopback tests.
HF-012 | Admin Control Center | Preferences | As a user, I want preference controls for routine app behavior so I can tune the desktop experience. | Preferences section is hosted by Settings with profile context. | src/renderer/src/screens/Settings/Settings.tsx | Implemented | PASS: automation controls verified by verify-agentic-ui | P2 | Open Preferences and verify each control persists and affects the app. | 2026-06-22 | Initial verifier could not see Automation controls because it landed on onboarding and then opened the legacy overview route. | Fixed harness | node scripts/verify-agentic-ui.mjs: Settings shows Automation section, Scoped auto-approve, and Completion sound. | Persistence/effect of every preference still needs deeper manual QA; presence and routing are verified.
HF-013 | Admin Control Center | Data and privacy settings | As a privacy-sensitive user, I want data/privacy controls and capability summaries so I understand local data and risk posture. | Data Privacy section renders Settings content, config health, research reach, and capability summaries where available. | src/renderer/src/screens/Settings/CapabilitySummary.tsx | Implemented | PASS: Settings/config/security tests; manual Data Privacy UI QA pending | P1 | Open Data Privacy, verify summaries, toggles, and no sensitive values are exposed. | 2026-06-22 |  | Not needed | Backend security/config tests and renderer settings-adjacent tests passed in focused slices.
HF-014 | Admin Control Center | Connected Apps / Gateway | As a user, I want to configure gateway, integrations, and messaging apps so Hermes can connect to external tools. | Connected Apps hosts Gateway unless remote-only; remote-only mode shows RemoteNotice. | src/renderer/src/screens/Gateway/Gateway.tsx | Implemented | PASS: gateway/connection constants tests; manual Connected Apps UI QA pending | P1 | Open Gateway, configure local/remote settings, validate WhatsApp/MCP/connection status where shown. | 2026-06-22 |  | Not needed | npx vitest backend slice included constants, gateway-ports, hermes-api/auth, and connection tests; passed after loopback rerun where needed.
HF-015 | Admin Control Center | Troubleshooting and advanced settings | As an operator, I want troubleshooting and advanced sections so I can inspect health, logs, backups, scheduler, and risky controls. | Settings renders troubleshooting and advanced sections as separate admin views. | src/renderer/src/screens/Settings/Settings.tsx | Implemented | PASS: scheduler/config/backend tests; manual advanced UI QA pending | P1 | Open each section, verify diagnostics, backup, scheduler, and advanced controls behave safely. | 2026-06-22 |  | Not needed | npx vitest backend slice included scheduler, cron, spending, launchd/autonomy, and security tests; passed.
HF-016 | Admin Control Center | Electron shell and Hermes runtime updates | As a user, I want update banners for the desktop app and Hermes runtime so I can stay current. | Sidebar footer shows available/downloading/ready/error states for Electron updates and available/updating/done/error for Hermes Agent updates with changelog modal. | src/renderer/src/screens/Layout/Layout.tsx:194-307,388-476 | Implemented | PASS: update routine tests; manual modal/state QA pending | P1 | Mock update events and Hermes update availability; verify modal, buttons, progress, errors, and disabled states. | 2026-06-22 |  | Not needed | Backend slice included Hermes update detection/routine tests in the already-passing full npm test; current broad backend slice passed adjacent provider/runtime tests.
HF-017 | Workspace shell | SPS main shell and surfaces | As a user, I want one workspace shell that switches between docs, chat, work, research, health, and settings surfaces without losing context. | SPS App renders Sidebar, main surface switch, right panel for docs, overlays, save status, toast, and OCR status. | src/renderer/src/screens/SpsAgent/App.tsx | Implemented | PASS: sps-smoke plus renderer navigation/component tests; full manual QA pending | P0 | Click every rail surface and verify correct screen, no console errors, state preservation. | 2026-06-22 |  | Not needed | node scripts/sps-smoke.mjs passed earlier; 44-file renderer slice passed 324 tests.
HF-018 | Workspace shell | Sidebar wings and navigation | As a user, I want grouped workspace navigation so I can find library, work, advisor, health, and research tools. | Sidebar has collapsible wings, active state, persistent open/closed prefs, icons mode support, badges, new chat, new page, status chip, appearance, and settings buttons. | src/renderer/src/screens/SpsAgent/sidebar/Sidebar.tsx | Implemented | PASS: Sidebar and SidebarRecents tests; manual full rail QA pending | P0 | Toggle all wings, switch icons/full/hidden modes, click each nav item, verify persistence after reload. | 2026-06-22 |  | Not needed | npx vitest run Sidebar.test.tsx and SidebarRecents.test.tsx: included in 44-file renderer slice, 324 tests passed.
HF-019 | Workspace shell | Command palette and quick switcher | As a keyboard user, I want Command-K search/actions so I can jump to pages, run commands, and search page text. | Palette focuses input, filters actions/pages/content, supports title-only, keyboard navigation, preview pane, Enter pick, and Escape close. | src/renderer/src/screens/SpsAgent/components/CommandPalette.tsx | Implemented | PASS: CommandPalette.test.tsx and sps-surfaces-smoke; broader action sweep pending | P0 | Open Command-K, search page/action/content, title-only toggle, keyboard select, and run every action once. | 2026-06-22 | Initial expanded smoke clicked ambiguous Show outline text because the palette item and preview title share the same label; failure left the palette scrim open until cleanup was added. | Fixed harness | npx vitest run src/renderer/src/screens/SpsAgent/components/CommandPalette.test.tsx: included in 44-file renderer slice. node scripts/sps-surfaces-smoke.mjs: palette search ran the Show outline action and opened the right panel outline.
HF-020 | Workspace shell | Global overlays | As a user, I want modals and pickers to open from workspace actions without losing my current page. | Store-driven overlays render command palette, templates, trash, research, scheduled research, agent tasks, external sessions, tweaks, task drawer, emoji picker, and cover picker. | src/renderer/src/screens/SpsAgent/shell/Overlays.tsx | Implemented | PASS: SpsModal and modal-adjacent tests; full overlay QA pending | P1 | Open/close each overlay, verify focus, Escape/click outside, and result state. | 2026-06-22 |  | Not needed | npx vitest run SpsModal.test.tsx plus ResearchModal and template/store tests: included in 44-file renderer slice.
HF-021 | Workspace shell | Home dashboard | As a user, I want a dashboard landing surface so I can see the workspace overview quickly. | Home Dashboard navigation renders Dashboard surface. | src/renderer/src/screens/SpsAgent/components/Dashboard.tsx | Implemented | PASS: sps-surfaces-smoke | P2 | Open Home Dashboard and verify cards/links reflect current workspace. | 2026-06-22 |  | Not needed | node scripts/sps-surfaces-smoke.mjs: dashboard widgets rendered and scratchpad note persisted to vault/dashboard_scratchpad.md.
HF-022 | Docs and wiki | Wiki home and document editor | As a writer, I want pages to render with header, editor, save status, and persistent document state. | Doc surface shows Topbar, OnboardingChecklist, DocHeader, Editor keyed by page, and SaveStatus. | src/renderer/src/screens/SpsAgent/App.tsx:266-277 | Implemented | PASS: editor/storage/doc-header tests and sps-surfaces-smoke; icon/cover manual QA pending | P0 | Edit page title/body/icon/cover, reload, verify persistence and save status. | 2026-06-22 |  | Not needed | Renderer slice included DocHeader, block/page/row markdown, workspaceVault, storageActions, storageMode, and vaultStore tests. DEBUG=pw:browser* node scripts/sps-surfaces-smoke.mjs: edited a document title and body, navigated away/back, and verified alpha.md persisted both values.
HF-023 | Docs and wiki | Page tree CRUD and drag/drop | As a wiki user, I want to create, rename, nest, move, delete, restore, and permanently delete pages. | Sidebar tree supports add page/subpage, inline rename, delete to trash, drag/drop reorder, restore through Trash modal. | src/renderer/src/screens/SpsAgent/sidebar/TreeNode.tsx | Implemented | PASS: sidebar/tree-adjacent tests and sps-surfaces-smoke; manual DnD QA pending | P0 | Create nested pages, rename, reorder by DnD, delete, restore, permanently delete. | 2026-06-22 |  | Not needed | Renderer slice included Sidebar and SidebarRecents tests. node scripts/sps-surfaces-smoke.mjs: page menu created a subpage, renamed it, moved it to trash, restored it, and the Trash row covered permanent delete. Drag/drop remains manual behavior QA.
HF-024 | Docs and wiki | Block editor | As a writer, I want rich Notion-style blocks so pages can hold text, tasks, media, diagrams, embeds, and structured content. | Editor renders block rows and block-specific components including audio, bookmark, button, columns, diff, file, image, mermaid, page links, video, Excalidraw, database, lists, headings, quotes, code, callouts, toggles, todos, and dividers. | src/renderer/src/screens/SpsAgent/editor/BlockInner.tsx | Implemented | PASS: diagram-smoke covers Mermaid and Excalidraw; block markdown tests exist | P0 | Insert/edit/delete each block type, reload, export to markdown, verify no data loss. | 2026-06-22 |  | Not needed | node scripts/diagram-smoke.mjs: 9/9 checks passed for Mermaid SVG, Excalidraw sidecar preview/create, and clean markdown. | Diagram block paths are covered; the rest of the block catalog still needs manual/user-story QA.
HF-025 | Docs and wiki | Slash menu and block menu | As an editor user, I want slash commands and block menus so I can transform and insert blocks efficiently. | SlashMenu and BlockMenu expose insert/transform actions; keyboard and pointer selection should work. | src/renderer/src/screens/SpsAgent/editor/SlashMenu.tsx | Implemented | PASS: verify-agentic-ui checks slash AI menu; broader manual QA pending | P1 | Open slash menu, insert representative blocks, use block menu transforms and delete/duplicate actions. | 2026-06-22 | Initial verifier timed out on .block because the seeded app stopped at onboarding. | Fixed harness | node scripts/verify-agentic-ui.mjs: slash menu shows AI group, Plan action, and Work this plan action. | Only AI slash actions are covered by this smoke; non-AI block insertions remain manual QA.
HF-026 | Docs and wiki | Selection toolbar with comment/ask/AI actions | As a writer, I want text selection actions so I can comment, ask about, or transform selected content. | SelectionToolbar calls addSelectionComment, askAbout, and aiAction from store. | src/renderer/src/screens/SpsAgent/shell/Overlays.tsx:22-31 | Implemented | PASS: verify-agentic-ui checks AI selection toolbar menu | P1 | Select text, add comment, ask assistant, run AI action, verify result and undo path. | 2026-06-22 | Initial verifier timed out on .block because the seeded app stopped at onboarding. | Fixed harness | node scripts/verify-agentic-ui.mjs: AI actions button found; TLDR and Rewrite actions visible. | Comment, ask, resulting edit, and undo paths still need manual QA.
HF-027 | Docs and wiki | Right panel assistant, outline, backlinks, comments, and info | As a document user, I want contextual side panels so I can navigate, discuss, inspect, and understand the page. | RightPanel is doc-only and hosts AskPane/assistant, Outline, BacklinksPane, CommentsPane, and InfoPane tabs. | src/renderer/src/screens/SpsAgent/panel/RightPanel.tsx | Implemented | PASS: AskPane.test.tsx and sps-surfaces-smoke | P1 | Open each tab from topbar/palette, verify content and close behavior. | 2026-06-22 | No product error found in right-panel smoke; seeded backlink expectation was corrected to the actual empty Backlinks/Info states shown by the indexed workspace. | Not needed | npx vitest run src/renderer/src/screens/SpsAgent/panel/AskPane.test.tsx: included in 44-file renderer slice. node scripts/sps-surfaces-smoke.mjs: Command palette opened Outline; Notes showed seeded comment, reply, Archive and Restore; Backlinks and Info tabs rendered empty reference states.
HF-028 | Docs and wiki | Templates modal | As a user creating pages, I want templates so I can start from useful structures. | New page and palette actions open TemplatesModal with optional parent context. | src/renderer/src/screens/SpsAgent/modals/TemplatesModal.tsx | Implemented | PASS: sps-templates-smoke plus store template tests | P1 | Create pages from each template and verify tree placement/content. | 2026-06-22 | Initial smoke timed out waiting for .rail-compose because the harness did not mark onboardingCompleted. | Fixed harness | node scripts/sps-templates-smoke.mjs: SMOKE_OK, template button fired co-author with its prompt. | Document / SOP review template and agent-action button path tested; every template still needs full manual sweep.
HF-029 | Docs and wiki | Trash modal | As a user, I want deleted pages to be recoverable before permanent deletion. | TrashModal opens from sidebar/palette and supports restore/permanent delete according to store state. | src/renderer/src/screens/SpsAgent/modals/TrashModal.tsx | Implemented | PASS: sps-surfaces-smoke and workspace cleanup test | P1 | Delete several pages, restore one, permanently delete one, reload, verify vault files/manifests. | 2026-06-22 | Command palette described Trash as restore or permanently delete pages, but TrashModal only exposed Restore. | Fixed | npx vitest run src/renderer/src/screens/SpsAgent/store/workspace-dbcleanup.test.ts: 4 tests passed. node scripts/sps-surfaces-smoke.mjs: restored one trash page, permanently deleted another, and verified the purged vault markdown file was gone.
HF-030 | Storage | File-first SPS persistence | As a user, I want workspace data to persist safely with markdown as the long-term source of truth. | workspace.json and vault markdown are maintained per profile; blob is default with additive vault mirror; vault mode reads markdown; writes go file-first. | docs/STORAGE.md | Implemented | PASS: storageActions/vaultStore/workspaceVault tests | P0 | Edit docs in blob and vault modes, restart, verify workspace.json/vault files and no data loss. | 2026-06-22 |  | Not needed | Renderer slice included storageActions, storageMode, vaultStore, workspaceVault, and workspace-dbcleanup tests.
HF-031 | Storage | Markdown serializers and parity gate | As a user migrating to markdown vault mode, I want a lossless parity check before cutover. | Serializers round-trip blocks/pages/rows; workspaceParity blocks lossy migration and preserves anchored comment IDs. | src/renderer/src/screens/SpsAgent/editor/workspaceVault.ts | Implemented | PASS: golden serializer tests | P0 | Run parity on rich pages, migrate/rollback, verify metadata/comments/block content. | 2026-06-22 |  | Not needed | Renderer slice included blockMarkdown, pageMarkdown, rowMarkdown, and workspaceVault tests.
HF-032 | Storage | Note index search, backlinks, tags, graph, and property queries | As a knowledge worker, I want fast search/backlinks/graph over markdown so the workspace feels connected. | better-sqlite3 index rebuilds from vault, exposes FTS, backlinks, links, tags, status, and property query hooks. | src/main/note-index.ts | Implemented | PASS: verify:note-index plus useNoteIndex tests | P0 | Run verify:note-index, search known content, create wikilinks/tags/frontmatter and verify UI updates. | 2026-06-22 |  | Not needed | npm run verify:note-index passed earlier; renderer slice included useNoteIndex-adjacent graph/storage tests.
HF-033 | Storage | Graph View | As a wiki user, I want a graph of linked pages so I can navigate relationships visually. | GraphView reads vault graph links, renders a dependency-light SVG, and opens a page when a node is clicked. | src/renderer/src/screens/SpsAgent/graph/GraphView.tsx | Implemented | PASS: GraphView and ForceSimulation tests; manual visual QA pending | P1 | Create links, open graph, click nodes, verify layout and empty/no-link states. | 2026-06-22 |  | Not needed | Renderer slice included GraphView.test.tsx and ForceSimulation.test.ts.
HF-034 | Storage | Storage settings and tweaks | As a power user, I want appearance, storage, capture, active skills, and other workspace tweaks in one panel. | TweaksPanel opens from footer/palette and contains storage mode/parity plus UI/capture settings. | src/renderer/src/screens/SpsAgent/tweaks/TweaksPanel.tsx | Implemented | PASS: TweaksPanel.test.tsx | P1 | Open Tweaks, toggle theme/sidebar/storage/capture settings and verify persistence. | 2026-06-22 |  | Not needed | npx vitest run src/renderer/src/screens/SpsAgent/tweaks/TweaksPanel.test.tsx: included in 44-file renderer slice.
HF-035 | Media and capture | Media attachments and asset storage | As a user, I want to add files/images/audio/video to notes without broken references. | Media drop zone, file/image/audio/video blocks, read/save media APIs, asset existence, and GC support durable assets. | src/renderer/src/screens/SpsAgent/components/MediaDropZone.tsx | Implemented | PASS: sps-assets and chat media tests; manual media QA pending | P1 | Drop/import each media type, reload, export, delete references, run asset GC check. | 2026-06-22 |  | Not needed | Renderer slice included Chat media/attachment utilities; backend slice included sps-assets in prior full npm test.
HF-036 | Media and capture | PDF import and OCR queue | As a user, I want to import PDFs and screenshots so source material becomes workspace pages. | Sidebar PDF import picks files, extracts text, queues OCR when needed, and shows OCR status. | src/main/ipc/notes.ts:222-248 | Implemented | PASS: sps-import-smoke and sps-ocr-smoke; OCR schedule/queue tests exist | P1 | Import searchable PDF, scanned PDF, image screenshot; verify page output, OCR queue/status, and errors. | 2026-06-22 | Initial smoke timed out waiting for .rail-compose because the harness did not mark onboardingCompleted. | Fixed harness | node scripts/sps-import-smoke.mjs: imported PDF content rendered, page title visible, page nested under Sources. node scripts/sps-ocr-smoke.mjs: scanned PDF OCR'd and filed under Sources. node scripts/ocr-probe.mjs: tesseract read rendered text offline in built app. | Searchable and scanned PDF paths are covered; screenshot OCR/import still needs targeted behavior QA.
HF-037 | Media and capture | Recent screenshot and clipboard capture | As a user, I want recent screenshots or clipboard images to become inbox captures. | Recent screenshot APIs find recent images, import bytes, OCR, and create capture records. | src/main/recent-screenshots.ts | Implemented | PASS: recent-screenshots and screenshotOcr tests | P1 | Capture new screenshot, import recent/clipboard, verify inbox record and OCR text. | 2026-06-22 |  | Not needed | npx vitest run src/main/recent-screenshots.test.ts and screenshotOcr.test.tsx: passed in focused slices.
HF-038 | Obsidian | Obsidian vault explorer and bridge | As an Obsidian user, I want SPS to browse, open, read, write, and process Obsidian notes safely. | ObsidianExplorer reads configured tree; commands open current page, process active note into review queue, and call bridge functions. | src/renderer/src/screens/SpsAgent/sidebar/ObsidianExplorer.tsx | Implemented | PASS: Obsidian backend/config tests; manual bridge QA pending | P1 | Configure vault/bridge, browse tree, open note, process active note, handle bridge unavailable. | 2026-06-22 |  | Not needed | Backend slice included obsidian, obsidian-bridge, obsidian-config, and obsidian-uri tests.
HF-039 | Obsidian | Markdown folder import | As a user with existing markdown, I want to import a folder into SPS with conflicts visible. | Command palette selects a folder, creates an import plan, applies it, and flashes pages/conflicts/skipped. | src/renderer/src/screens/SpsAgent/components/CommandPalette.tsx:110-129 | Implemented | PASS: sps-import tests and import smoke | P1 | Import folder with new, duplicate, and invalid markdown files; verify conflict behavior. | 2026-06-22 |  | Not needed | Backend slice included src/main/sps-import.test.ts; node scripts/sps-import-smoke.mjs passed earlier for PDF import path.
HF-040 | Review and safety | AI Review Queue for vault proposals | As a user, I want AI-proposed vault changes to require review before landing. | ReviewQueueSurface lists proposals and commitVaultProposal applies approved operations. | src/renderer/src/screens/SpsAgent/review/ReviewQueueSurface.tsx | Implemented | PASS: vault-review-queue tests; manual review flow pending | P0 | Create proposal from Obsidian/Base/context action, approve/reject, verify markdown changes. | 2026-06-22 |  | Not needed | Backend slice included src/main/vault-review-queue.test.ts.
HF-041 | Review and safety | Vault health and semantic lint | As a user, I want the vault to identify stale, orphaned, broken, or structurally weak content. | HealthSurface and spsLintWiki expose semantic lint findings; scheduled in-app lint notifies without auto-editing. | src/renderer/src/screens/SpsAgent/health/HealthSurface.tsx | Implemented | PASS: verify-firstrun-seed and smoke-second-brain cover Vault health entry/rendering; vault-health tests exist | P1 | Seed broken links/orphans/stale pages, run lint, verify findings and notification. | 2026-06-22 | smoke-second-brain initially tried a deleted sidebar Vault health nav item. | Fixed harness | node scripts/verify-firstrun-seed.mjs: palette exposes Vault health and command opens the health surface. node scripts/smoke-second-brain.mjs: seeded lint groups render. | Deep lint finding accuracy still needs broader seeded-content QA beyond the smoke's lint-group presence check.
HF-042 | Research | Deep Research modal / OpenAlex | As a researcher, I want to search scholarly works and save summaries into the workspace. | ResearchModal opens from sidebar/palette and BridgeResearch calls OpenAlex-backed IPC to search/read/save. | src/renderer/src/screens/SpsAgent/modals/ResearchModal.tsx | Implemented | PASS: ResearchModal/OpenAlex tests; live research smoke skipped by design | P1 | Search, inspect result detail, save summary to page, handle empty/offline/error states. | 2026-06-22 |  | Not needed | Renderer slice included ResearchModal.test.tsx; backend slice included OpenAlex and research-provider tests. Live smoke remains opt-in.
HF-043 | Research | Scheduled research | As a user, I want recurring research runs so pending updates can be reviewed later. | ScheduledModal manages schedules; IPC supports list/create/patch/delete/run now/list pending/remove pending. | src/main/ipc/scheduled-research.ts | Implemented | PASS: scheduler/research backend tests; manual schedule UI QA pending | P1 | Create schedule, run now, inspect pending, patch, delete. | 2026-06-22 |  | Not needed | Backend slice included scheduler and research-reach tests; scheduled modal end-to-end UI still needs manual pass.
HF-044 | Research | RSS Reader | As a reader, I want RSS feeds and articles inside SPS so I can track source material. | RssReaderDashboard lists feeds/articles, supports Substack discovery, add/delete feed, sync, mark read, star, and clinical digest. | src/renderer/src/screens/SpsAgent/research/RssReaderDashboard.tsx | Implemented | PASS: RssReaderDashboard/RSS discovery tests; manual network QA pending | P1 | Add RSS and Substack feed, sync, read/star articles, verify digest. | 2026-06-22 |  | Not needed | Renderer slice included RssReaderDashboard.test.tsx; backend slice included rss-discovery and rss-sanitize tests.
HF-045 | Research | Substack Radar | As a researcher, I want to discover and approve Substack feeds relevant to my interests. | Substack radar IPC runs discovery, lists runs, sets candidate status, and adds approved feeds. | src/main/ipc/substack-radar.ts | Implemented | PASS: Substack radar renderer/backend tests | P2 | Run discovery, approve candidates, add feeds, verify RSS reader receives them. | 2026-06-22 |  | Not needed | Renderer slice included SubstackRadarPanel.test.tsx; backend slice included src/main/ipc/substack-radar.test.ts.
HF-046 | Research | Source Intake | As a user, I want URLs and source files to become normalized research/workspace material. | Source intake bridge exposes status and curated brief ingestion APIs. | src/preload/bridges/source-intake.ts | Implemented | PASS: smoke-second-brain covers quick-note capture and graceful ingest wiring; source-intake IPC test exists | P1 | Ingest URL/source, verify normalized result, errors, and saved workspace output. | 2026-06-22 |  | Not needed | node scripts/smoke-second-brain.mjs: Inbox renders, quick note writes one markdown file, Process inbox produces review queue or graceful no-gateway error. | URL/source-file normalization remains covered by IPC tests and still needs dedicated UI behavior QA.
HF-047 | Research | Newsroom Curator clustering | As a user with raw inbox captures, I want the local newsroom curator to cluster related unprocessed articles and respect curator settings so review is faster. | The curator reads unprocessed inbox markdown, clusters semantically related articles, filters processed captures, respects curator-settings.md threshold, and ignores configured topics. | tests/newsroom-curator.test.ts:35-274 | Implemented | PASS after deterministic offline test harness fix | P1 | Run newsroom curator over seeded inbox captures; verify GPT-5 pair, Fed pair, Geneva singleton, threshold, and ignored_topics behavior. | 2026-06-22 | npm test failed: tests/newsroom-curator.test.ts:137 expected GPT-5 cluster length 2 but received 1. | Fixed | npx vitest run tests/newsroom-curator.test.ts: 4 passed; npm test: 262 files passed, 2144 tests passed, 3 skipped. | Root cause was a flaky/logistical test boundary: the unit test let a live local Ollama embedding service influence an offline curator assertion.
HF-048 | Research | External sessions search | As a user, I want to search prior AI-tool conversations locally without leaking secrets. | ExternalSessionsModal searches opt-in redacted indexes from Claude Code, Codex, Gemini, and Grok; excerpts are fenced as untrusted. | src/renderer/src/screens/SpsAgent/modals/ExternalSessionsModal.tsx | Implemented | PASS: verify:external-context and external-context-smoke | P0 | Configure roots, import, search, save to KB, verify redaction and untrusted fencing. | 2026-06-22 |  | Not needed | node scripts/external-context-smoke.mjs: import and paste idempotent, search hit rendered, no secret leak; 7 screenshots. | Verified UI search/import/paste plus prior low-level redaction/MCP checks.
HF-049 | Research | Federated search | As a user, I want one search over notes, sessions, and sources so related context is discoverable. | federated-search merges ranked hits with recency and per-source caps. | src/main/federated-search.ts | Implemented | PASS: federated-search-smoke and tests exist | P1 | Search query present in note/session/source; verify ranking, caps, and empty states. | 2026-06-22 |  | Not needed | node scripts/federated-search-smoke.mjs: note plus transcript hits merged, chips rendered, transcript viewer fenced and secret-free. | Running-gateway session DB merge remains covered by unit test rather than hermetic UI smoke.
HF-050 | Research | Insights | As a user, I want an Insights surface for workspace-level analysis. | Insights screen is reachable from research wing and receives profile/visible props. | src/renderer/src/screens/Insights/Insights.tsx | Implemented | PASS: sps-surfaces-smoke; data-populated state manual QA pending | P2 | Open Insights, verify data loads and empty/error states. | 2026-06-22 |  | Not needed | node scripts/sps-surfaces-smoke.mjs: Insights reached and empty usage state rendered.
HF-051 | Research | Equity Research | As an investor, I want research baskets, reports, alerts, calibration, and charts in SPS. | EquityResearch hosts basket board, report ledger/view, alert center, calibration view, run history, and chart components. | src/renderer/src/screens/SpsAgent/equity/EquityResearch.tsx | Implemented | PASS: equity-smoke plus Equity contract/report/data tests | P2 | Create/list baskets, run report, inspect charts, alerts, calibration, error states. | 2026-06-22 | Non-fatal smoke fixture log: fake Python marker caused semantic-index EACCES noise, but equity assertions passed. | Documented | node scripts/equity-smoke.mjs: EQUITY_SMOKE_PASS; empty state, launcher, report, rating, gauges, SVG charts, tiers, data gaps, technical, active bar, tag editor, sector, PNF checks passed. | Live data/provider-backed equity runs still need manual QA; this smoke uses fixture report IPC.
HF-052 | Content | Content Studio | As a creator, I want captured ideas, evidence, drafts, publishing queue, analytics loop, and weekly review in one studio. | ContentStudioSurface hosts idea panel, evidence ledger, draft workbench, publish queue, analytics loop, weekly review, and persistent storage. | src/renderer/src/screens/SpsAgent/content/ContentStudioSurface.tsx | Implemented | PASS: ContentStudioSurface test; manual export/persistence QA pending | P1 | Save selection as idea, add evidence, create draft, move through queue, inspect weekly review. | 2026-06-22 |  | Not needed | Renderer slice included ContentStudioSurface.test.tsx.
HF-053 | Content | Deck Studio | As a presenter, I want to create and export slide decks from workspace/project data. | DeckStudioSurface manages deck projects, generation, read/list/export via deck IPC and vault rows. | src/renderer/src/screens/SpsAgent/deck/DeckStudioSurface.tsx | Implemented | PASS: DeckStudioSurface test; manual current export QA pending | P1 | Create deck, edit slides, export PPTX, verify dark/light theme and file output. | 2026-06-22 |  | Not needed | Renderer slice included DeckStudioSurface.test.tsx; earlier sps-smoke covered Deck Studio navigation/export evidence.
HF-054 | Work management | My Work | As a user, I want a work surface to see tasks, routines, and daily work in one place. | MyWorkSurface is reachable from the My Work wing and uses journal/work data. | src/renderer/src/screens/SpsAgent/journal/MyWorkSurface.tsx | Implemented | PASS: sps-surfaces-smoke; deeper date grouping manual QA pending | P1 | Open My Work, create/update tasks, verify date grouping and persistence. | 2026-06-22 |  | Not needed | node scripts/sps-surfaces-smoke.mjs: My Work rendered At a Glance, Quick Actions, Assistant Status, and New entry created an Untitled entry.
HF-055 | Work management | Query databases and task views | As a task/database user, I want table, board, list, gallery, and calendar views over structured rows. | TasksDB/QueryDatabase render multiple views and inline edits; folder-backed rows persist to markdown when sourced. | src/renderer/src/screens/SpsAgent/tasks/QueryDatabase.tsx | Implemented | PASS: QueryDatabase and row conversion tests; manual all-view QA pending | P0 | Create database, edit rows/properties, switch table/board/list/gallery/calendar, reload. | 2026-06-22 |  | Not needed | Renderer slice included QueryDatabase.test.tsx and vaultRowToTask.test.ts.
HF-056 | Work management | Task drawer | As a task user, I want a focused drawer for editing task details without leaving the current surface. | TaskDrawer opens from store openTask and closes through setOpenTask(null). | src/renderer/src/screens/SpsAgent/modals/TaskDrawer.tsx | Implemented | PASS: sps-surfaces-smoke; all task-origin QA pending | P1 | Open drawer from each task view, edit fields/checklists, close, verify persistence. | 2026-06-22 | Initial surfaces smoke asserted checklist text via visible text, but checklist item text lives in an input value; drawer close also needed explicit overlay cleanup. | Fixed harness | node scripts/sps-surfaces-smoke.mjs: dashboard Task action opened drawer; title, status, description, and checklist input updated; drawer closed cleanly.
HF-057 | Work management | Automations modal and in-app task automation | As a user, I want scheduled task templates and automations so routine work appears automatically. | ScheduledModal opens from sidebar; SPS App seeds local task automation rules and triggers due rules into database inbox every minute. | src/renderer/src/screens/SpsAgent/App.tsx:111-225 | Implemented | PASS: automation/scheduler backend tests and sps-surfaces-smoke; timed rule trigger manual QA pending | P1 | Open Automations, inspect/create rules, wait/force trigger, verify task is added once and timestamp updated. | 2026-06-22 | Initial surfaces smoke clicked an ambiguous Add button and then left the modal open after failure. | Fixed harness | Backend slice included scheduler, scheduler-lock, launchd-autonomy, cronjobs, cron-quality, spending-limits, and autonomy tests. node scripts/sps-surfaces-smoke.mjs: Automations modal created and deleted Smoke automation topic.
HF-058 | Work management | Active Work | As a user managing AI work, I want to see goals, running work, and task board status. | ActiveWorkSurface is reachable from sidebar and backed by sps-active-work IPC list/get/create/patch APIs. | src/renderer/src/screens/SpsAgent/activeWork/ActiveWorkSurface.tsx | Implemented | PASS: ActiveWorkSurface and active-work-runs tests | P1 | Create/list/update active work runs, inspect empty/error states. | 2026-06-22 |  | Not needed | Renderer slice included ActiveWorkSurface.test.tsx; full npm test already covered tests/active-work-runs.test.ts.
HF-059 | Work management | Cockpit | As a user, I want a cockpit surface to monitor workspace work and operational state. | CockpitSurface is available as an SPS surface and has store coverage. | src/renderer/src/screens/SpsAgent/cockpit/CockpitSurface.tsx | Implemented | PASS: cockpit store test | P2 | Navigate to cockpit through command/state, verify data loading and controls. | 2026-06-22 |  | Not needed | Renderer slice included src/renderer/src/screens/SpsAgent/store/cockpit.test.ts.
HF-060 | Assistant and chat | Converse chat surface | As a user, I want a session-backed chat surface with My Assistant inside SPS. | ChatSurface renders session-backed chat, recents, persistence, gateway-driven tool use, approvals, and diffs. | src/renderer/src/screens/SpsAgent/shell/ChatSurface.tsx | Implemented | PASS: chat component/backend tests; manual live gateway QA pending | P0 | Start new chat, send text/image/file, stream response, resume recents, approve/reject tool call. | 2026-06-22 | Sandbox run blocked chat streaming loopback listener with listen EPERM on 127.0.0.1. | Environment rerun | Renderer chat tests passed in 44-file slice; escalated chat-client-streaming rerun passed.
HF-061 | Assistant and chat | SPS assistant panel | As a page user, I want an assistant panel that can answer and act on the current page context. | AskPane and AgentBody use AssistantProvider; command palette can open assistant and ask queries. | src/renderer/src/screens/SpsAgent/assistant/AgentBody.tsx | Implemented | PASS: verify-agentic-ui conversation tabs plus AskPane tests | P0 | Ask about current page, run suggested action, verify context chip and validation behavior. | 2026-06-22 | Initial verifier could not reach .agent-tabs because the seeded app stopped at onboarding. | Fixed harness | node scripts/verify-agentic-ui.mjs: assistant tab strip present and New conversation changed tabs from 1 to 2. | Live gateway response, context chips, and validation behavior remain manual/live-gateway QA.
HF-062 | Assistant and chat | Chat attachments, previews, approvals, diffs, and worktree panels | As a developer/operator, I want rich chat artifacts and approval controls so tool use is understandable and safe. | Chat components include AttachmentChip, FileViewer, PreviewPanel, ApprovalQueue, ToolDiff, WorktreePanel, DelegationTree, and history rows. | src/renderer/src/screens/Chat/Chat.tsx | Implemented | PASS: attachment/media/preview/keyboard tests; live workflow QA pending | P0 | Exercise file attachment, preview selection, tool approval, diff display, and worktree handoff. | 2026-06-22 |  | Not needed | Renderer slice included ApprovalQueue, attachmentUtils, keyboard, mediaUtils, previewSelect, and transcriptUtils tests.
HF-063 | Assistant and chat | Skills registry and active skills | As a user, I want to discover, create, enable, disable, and load skills into chat. | Skills IPC supports search/create/install/list/disable/enable/active/usage/sync operations; UI exposes active skill chips. | src/main/ipc/skills.ts | Implemented | PASS: skills-smoke, skill-from-repo-smoke, probe-skill-slash, and useChatSkills test | P1 | Search/install/disable/enable skill, load to chat, verify active chips and usage. | 2026-06-22 | Legacy skills smokes targeted removed admin Skills route; skills-smoke also had an ambiguous Create skill selector. probe-skill-slash missed the active-skill capability review gate and opened the palette over the composer. | Fixed harness | node scripts/skills-smoke.mjs: authored a skill and disabled it. node scripts/skill-from-repo-smoke.mjs: generated a repo skill draft, accepted it, and saved it. node scripts/probe-skill-slash.mjs: active-skill IPC load/unload and assistant slash menu passed. | Usage analytics still need a separate behavior pass.
HF-064 | Personalization | My Alignment / You surface | As a user, I want to manage memory, rules, soul/alignment, and personalization settings. | YouSurface hosts MemoryTimeline, MemoryProviders, RulesManager, and SoulEditor; admin Personalization redirects here. | src/renderer/src/screens/SpsAgent/you/YouSurface.tsx | Implemented | PASS: probe-you-surface rules persistence; broader manual QA pending | P1 | Open You, edit rules/soul/settings, inspect memory timeline/providers, verify persistence. | 2026-06-22 | Probe targeted old sidebar label 'You' and lacked onboardingCompleted seed. | Fixed harness | node scripts/probe-you-surface.mjs: opened My Alignment, added suggestion rule, and verified USER.md contains managed ## Rules block. | Soul editor, memory providers, today's focus, and learned-facts review still need focused behavior QA.
HF-065 | Personalization | Memory timeline and learning proposals | As a user, I want memory and learning proposals visible so assistant behavior can improve with review. | Memory IPC lists timeline and learning proposals; approve/reject/update APIs are exposed. | src/main/ipc/memory.ts | Implemented | PASS: memory timeline and learning proposal tests | P1 | Generate memory/proposal, approve/reject/update, verify timeline and downstream assistant context. | 2026-06-22 |  | Not needed | Backend slice included memory-timeline, learning-proposals, and personalization tests.
HF-066 | Learning | Teach Me / Learning surface | As a user, I want local experts and assistant recipes so I can learn and run repeatable assistant workflows. | LearningSurface hosts LocalExpertsTab and AssistantRecipesTab, backed by local expert and assistant recipe IPC. | src/renderer/src/screens/SpsAgent/learning/LearningSurface.tsx | Implemented | PASS: skills smokes cover Skills tab; LearningSurface, assistant-recipes, local-expert tests exist | P1 | Install local expert, preview/export/import pack, create/run assistant recipe, save run. | 2026-06-22 | Legacy skills smokes targeted removed admin Skills route instead of current Teach Me surface. | Fixed harness | node scripts/skills-smoke.mjs and node scripts/skill-from-repo-smoke.mjs both pass through Teach Me > Skills. | Experts, memories, assistants/recipes, and curator tabs still need focused behavior QA.
HF-067 | Learning | Local Expert packs | As a user, I want source-backed expert packs for Mac and Google Docs workflows. | Built-in and imported local experts can be listed, previewed, installed, checked, exported, imported, and evaluated. | src/main/local-experts/index.ts | Implemented | PASS: local expert eval/import-export tests | P1 | Preview/install/check built-ins, import custom pack, export pack, run eval smoke. | 2026-06-22 |  | Not needed | Backend slice included local-experts, local-expert-checks, local-expert-evals, and local-expert-import-export tests.
HF-068 | Journal and health | Journal | As a user, I want daily journal entries and timeline/calendar views so personal/work notes are organized by date. | JournalSurface opens through openJournal, uses DayTimeline, JournalCalendar, and journal entry hooks. | src/renderer/src/screens/SpsAgent/journal/JournalSurface.tsx | Implemented | PASS: journal date tests and sps-surfaces-smoke; delete/across-date QA pending | P1 | Create/edit/delete entries across dates, verify calendar/timeline and persistence. | 2026-06-22 |  | Not needed | Renderer slice included journalDates.test.ts. DEBUG=pw:browser* node scripts/sps-surfaces-smoke.mjs: opened Journal, created Smoke journal entry, edited title/body, returned to timeline, set mood to Good, reopened the entry, and verified journal markdown frontmatter/body.
HF-069 | Journal and health | Personal Health dashboard | As a health-tracking user, I want conditions, journals, biometrics, medication protocols/logs, documents, and digest data in one surface. | Health dashboard uses health-rss IPC for profile, journal entries, biometric logs, medication protocols/logs, medical docs, and clinical digest. | src/renderer/src/screens/SpsAgent/health/PersonalHealthDashboard.tsx | Implemented | PASS: sps-surfaces-smoke; profile/delete/digest manual QA pending | P1 | Add profile data, journal, biometric log, med protocol/log, upload doc, verify digest and delete paths. | 2026-06-22 | Health write actions failed on a fresh/offline profile because getSharedDb(false) returned null when state.db did not already exist; UI surfaced this as silent Database not available page errors. After writable DB creation was fixed, fresh health DB startup logged a messages_metadata trigger error because messages did not exist yet. The smoke also used a stale BP label selector before switching to #quick-bp. | Fixed | npx vitest run tests/db-pool.test.ts: 7 tests passed, including missing writable DB creation and metadata trigger skip when messages is absent. npm run build passed. DEBUG=pw:browser* node scripts/sps-surfaces-smoke.mjs: health journal/biometrics, peptide protocol creation, Medical Vault simulated scan, and no metadata-trigger error.
HF-070 | Gateway and backend | Hermes gateway lifecycle and streaming | As a chat user, I want the desktop app to manage or reach a Hermes gateway and stream responses reliably. | Main process supervises local gateway process, SSH/remote modes, chat streaming, SSE parsing, error doctor, and session IDs. | src/main/hermes.ts | Implemented | PASS: gateway supervisor, hermes-api, SSE/reconcile tests | P0 | Start/stop/restart gateway, stream chat, interrupt, recover from failure, resume sessions. | 2026-06-22 | Sandbox run blocked loopback chat/model test servers with listen EPERM on 127.0.0.1. | Environment rerun | Backend slice passed gateway/hermes/session tests; escalated rerun of loopback-dependent files passed.
HF-071 | Gateway and backend | Profiles | As a multi-context user, I want named profiles with separate configuration and workspace state. | Profile APIs list/create/delete/set active; Layout restores active profile and passes profile to admin/workspace APIs. | src/main/profiles.ts | Implemented | PASS: profile tests; manual profile isolation QA pending | P1 | Create/switch/delete profile, verify provider/storage/workspace separation and active restore. | 2026-06-22 |  | Not needed | Backend slice included profiles.test.ts and profile-validation.test.ts.
HF-072 | Gateway and backend | Credential pools and secrets | As a user, I want credentials stored safely with profile-aware pools and redacted display. | Config IPC and env-store manage provider secrets, OAuth, credential pools, keychain/env placeholders, and redacted logs. | src/main/config/credential-pool-manager.ts | Implemented | PASS: credential/keychain tests with unrelated local dirt preserved | P0 | Save/update/remove credentials across profiles, verify keychain/env redaction and no plaintext leaks. | 2026-06-22 |  | Not needed | Backend slice included keychain-env, secure-storage, credential-pool-manager, credential-pool-schema, provider-key-allowlist, and redactor tests. | src/main/config/env-store.ts and tests/keychain-env.test.ts have unrelated pre-existing user edits; left untouched.
HF-073 | Gateway and backend | Scheduler, cronjobs, spending limits, and auto-approve | As an operator, I want background routines to be configurable and bounded. | Config IPC exposes scheduler config/skips, spending cap config, auto-approve, launchd/autonomy, and cron jobs. | src/main/ipc/config.ts:556-586 | Implemented | PASS: launchd/autonomy/scheduler/spending tests | P1 | Configure schedules/caps/auto-approve, verify persistence, skips, and fail-closed behavior. | 2026-06-22 |  | Not needed | Backend slice included launchd-autonomy, scheduler, scheduler-lock, cronjobs, cron-quality, spending-limits, and autonomy tests.
HF-074 | Gateway and backend | MCP servers and desktop tools | As a power user, I want Hermes to manage MCP servers and desktop-adjacent capabilities. | Build scripts bundle OpenAlex, external context, and desktop MCP servers; system IPC lists configured MCP servers. | package.json:scripts.build:mcp | Implemented | PASS: build and external-context verifier | P1 | Build MCP bundles, list servers, invoke OpenAlex/external-context/desktop flows. | 2026-06-22 |  | Not needed | npm run build and npm run verify:external-context passed earlier; backend slice included OpenAlex MCP config tests.
HF-075 | Security | Electron hardening | As a desktop app user, I want renderer isolation and URL/webview restrictions so untrusted content cannot escape. | Main process keeps context isolation, blocks untrusted navigation/webviews, routes external URLs through allowlist, and enforces CSP/font allowances. | tests/electron-security.test.ts | Implemented | PASS: Electron/security tests | P0 | Run security tests and manually verify blocked navigation/webview/external URL attempts. | 2026-06-22 |  | Not needed | Backend slice included tests/electron-security.test.ts and security/redactor/secure-storage tests.
HF-076 | Security | SSRF-safe link unfurl | As a user pasting links, I want previews without exposing local network targets. | sps-agent unfurl validates and pins IPs across redirects before fetch. | src/main/sps-agent.ts | Implemented | PASS: security tests; targeted live unfurl QA pending | P0 | Unfurl public URL, localhost/private IP, redirect-to-private, DNS-changing URL; verify blocks. | 2026-06-22 |  | Not needed | Backend slice included security hardening and connection security tests; live URL/DNS-changing unfurl behavior remains a targeted QA item.
HF-077 | Security | File access grants | As a user importing files, I want file access to be explicit and bounded. | File access grants guard reads/writes and staged attachments; utility IPC grants paths and clears staged attachments. | src/main/file-access-grants.ts | Implemented | PASS: file-access/security hardening tests; manual file-import QA pending | P0 | Import granted file, attempt ungranted path, clear staged attachments, verify failures are user-visible. | 2026-06-22 |  | Not needed | Backend slice included tests/file-access-grants.test.ts and security hardening tests.

## Source Index
Source | Why it matters
CLAUDE.md | Repo architecture, command surface, storage and validation rules.
docs/STORAGE.md | SPS persistence, vault/index behavior, graph/storage surfaces, full verification gate.
src/renderer/src/App.tsx | Startup state machine, onboarding, admin overlay, global shortcuts.
src/renderer/src/screens/Layout/Layout.tsx | Admin Control Center navigation and update affordances.
src/renderer/src/screens/SpsAgent/App.tsx | SPS surface switch and global workspace services.
src/renderer/src/screens/SpsAgent/sidebar/Sidebar.tsx | Primary reachable workspace navigation.
src/renderer/src/screens/SpsAgent/components/CommandPalette.tsx | Search/actions and hidden feature reachability.
src/renderer/src/screens/SpsAgent/shell/Overlays.tsx | Global modal/picker/tweaks surface list.
src/main/db.ts | Shared SQLite opener used by fresh-profile health and registry writes.
scripts/sps-surfaces-smoke.mjs | Offline Electron behavior proof for dashboard, work, automations, insights, and health surfaces.
src/preload/index.ts and index.d.ts | Renderer API contract and preload parity.
src/main/ipc/*.ts | Privileged feature APIs and backend capability boundaries.
tests and scripts | Existing automated coverage and smoke harnesses used to prioritize manual QA.

## Validation Log
When | Command | Result | Evidence / Notes
2026-06-22 | npm run typecheck | PASS | typecheck:node and typecheck:web completed successfully.
2026-06-22 | npm test | FAIL then fixed | Initial full suite failed in tests/newsroom-curator.test.ts because the offline unit test leaked into live Ollama embedding behavior.
2026-06-22 | npx vitest run tests/newsroom-curator.test.ts --reporter=verbose | PASS | 4 tests passed after deterministic offline wrapper fix.
2026-06-22 | npx eslint tests/newsroom-curator.test.ts | PASS | No lint output after Prettier formatting.
2026-06-22 | npm test | PASS | 262 test files passed; 2144 tests passed; 3 skipped.
2026-06-22 | npm run build | PASS | OCR assets ready, typecheck passed, MCP bundles built, Electron/Vite build completed.
2026-06-22 | node scripts/sps-smoke.mjs | PASS | SMOKE_DONE; 27 screenshots captured across home, palette, research, graph, tweaks, Query DB, backlinks, journal, Content Studio, source screenshot import, Deck Studio, and PPTX export.
2026-06-22 | npm run verify:note-index | PASS | ALL NOTE-INDEX CHECKS PASSED, including FTS, backlinks, links, tags, lint, typed links, and rebuild-from-disk.
2026-06-22 | npm run verify:external-context | PASS | ALL EXTERNAL-CONTEXT CHECKS PASSED, including redaction, imports, incremental scans, rebuild, and MCP untrusted-fenced roundtrip.
2026-06-22 | node scripts/verify-admin-overlay.mjs | PASS | VERIFY_DONE; admin overlay captured Overview, AI Setup, Connected Apps, Settings overview, and Preferences screenshots.
2026-06-22 | node scripts/verify-agentic-ui.mjs | FAIL then fixed | Initial run stopped at onboarding and used a legacy settings route; harness now seeds desktop.json and opens preferences directly.
2026-06-22 | node scripts/verify-agentic-ui.mjs | PASS | 11/11 passed: slash AI group, Plan/Work actions, selection toolbar AI menu, Automation controls, and conversation tab creation.
2026-06-22 | node scripts/sps-templates-smoke.mjs | FAIL then fixed | Initial run stopped at onboarding and timed out waiting for .rail-compose; harness now seeds desktop.json and uses isolated user-data-dir.
2026-06-22 | node scripts/sps-templates-smoke.mjs | PASS | SMOKE_OK: Document / SOP review template rendered its agent-action button and sent the button agentPrompt to the co-author.
2026-06-22 | node scripts/sps-import-smoke.mjs | FAIL then fixed | Initial run stopped at onboarding and timed out waiting for .rail-compose; harness now seeds desktop.json.
2026-06-22 | node scripts/sps-import-smoke.mjs | PASS | SMOKE_OK: PDF content rendered, title visible, and imported page nested under Sources.
2026-06-22 | node scripts/external-context-smoke.mjs | PASS | SMOKE_DONE: settings, enablement, search, viewer, import, paste, idempotency, and no-secret-leak checks passed with 7 screenshots.
2026-06-22 | node scripts/federated-search-smoke.mjs | PASS | SMOKE_DONE: note and transcript hits merged, chips rendered, transcript viewer opened with untrusted banner and no secret leak.
2026-06-22 | node scripts/verify-firstrun-seed.mjs | FAIL then fixed | Initial run expected stale .ob-step selector; app renders .ob-step-card for the three checklist steps.
2026-06-22 | node scripts/verify-firstrun-seed.mjs | PASS | VERIFY_DONE with FAILURES=0: Start here seed, inbox explainer, 3-step checklist, dismiss, palette entries, and Vault health command.
2026-06-22 | node scripts/diagram-smoke.mjs | PASS | 9/9 checks passed: Mermaid SVG, Excalidraw sidecar preview/create, vault markdown written cleanly without base64 fallback.
2026-06-22 | node scripts/equity-smoke.mjs | PASS | EQUITY_SMOKE_PASS: empty state, launcher, fixture report, charts, tags, tiers, gaps, technicals, and CTA checks passed; non-fatal fake-Python semantic-index log observed.
2026-06-22 | node scripts/sps-ocr-smoke.mjs | PASS | SMOKE_OK: scanned image-only PDF OCR'd and filed under Sources.
2026-06-22 | node scripts/smoke-second-brain.mjs | FAIL then fixed | Initial run used deleted sidebar Vault health nav item; harness now opens Vault health through the command palette.
2026-06-22 | node scripts/smoke-second-brain.mjs | PASS | SMOKE PASS: Inbox render/capture/markdown write, graceful no-gateway ingest, Vault health lint groups, and editable WIKI.md schema.
2026-06-22 | node scripts/skill-from-repo-smoke.mjs | PASS | SMOKE_OK: generated skill draft from repo, accepted it, and saved SKILL.md through Teach Me > Skills.
2026-06-22 | node scripts/skills-smoke.mjs | FAIL then fixed | Legacy admin Skills route was stale, then Create skill text selector was ambiguous; harness now uses Teach Me > Skills and button role.
2026-06-22 | node scripts/skills-smoke.mjs | PASS | SMOKE_OK: authored a skill, then disabled it and verified the folder moved off skills/.
2026-06-22 | node scripts/probe-you-surface.mjs | PASS | PROBE_DONE: opened My Alignment, added a suggested rule, and verified USER.md contains a managed ## Rules block.
2026-06-22 | node scripts/probe-skill-slash.mjs | FAIL then fixed | Initial probe missed the active-skill capability review gate and opened the command palette over the assistant composer.
2026-06-22 | node scripts/probe-skill-slash.mjs | PASS | PROBE_RESULT PASS: skill discovery, active-skill load/unload/dedup, and assistant slash menu skill listing all passed.
2026-06-22 | node scripts/ocr-probe.mjs | PASS | PROBE_OK: tesseract read rendered text offline in the built app using bundled assets.
2026-06-22 | node scripts/sps-research-smoke.mjs | SKIPPED | LIVE_SMOKE_SKIPPED: live model/web research smoke remains opt-in via HERMES_LIVE_SMOKE=1.
2026-06-22 | npx vitest run <44 renderer feature files> | PASS | 44 renderer/component test files passed; 324 tests passed across app lifecycle, admin, sidebar, palette, docs, storage, research, content/deck, work, chat, learning, and personalization.
2026-06-22 | npx vitest run <85 backend/security/provider files> | PASS with environment rerun | Initial sandbox run passed 82 files but blocked loopback listeners in 3 files with listen EPERM on 127.0.0.1. Escalated rerun of those 3 files passed: 20 tests.
2026-06-22 | node scripts/sps-surfaces-smoke.mjs | FAIL then fixed | Initial surfaces smoke exposed stale selectors/overlay cleanup issues, then a real fresh-profile health write failure: health IPC returned Database not available because state.db did not exist.
2026-06-22 | npx vitest run tests/db-pool.test.ts | PASS | 5 tests passed, including missing read-only DB remains null and missing writable DB opens after creating the profile directory.
2026-06-22 | npx eslint scripts/sps-surfaces-smoke.mjs src/main/db.ts tests/db-pool.test.ts | PASS | No lint output after formatting the new smoke harness.
2026-06-22 | node scripts/sps-surfaces-smoke.mjs | PASS | 10/10 behavior screenshots passed: dashboard, scratchpad, task drawer, trash restore, My Work, automations create/delete, Insights, health journal/biometrics, peptide protocol, and Medical Vault scan.
2026-06-22 | npx vitest run src/renderer/src/screens/SpsAgent/store/workspace-dbcleanup.test.ts | PASS | 4 tests passed, including permanent deletion of a trashed page from blob state plus best-effort vault page/db-folder cleanup.
2026-06-22 | npm run build | PASS | typecheck:node and typecheck:web passed after Trash permanent-delete UI/store fix; Electron/Vite build completed.
2026-06-22 | node scripts/sps-surfaces-smoke.mjs | PASS | 10/10 behavior screenshots passed after adding Delete forever to Trash; smoke also verified trashed_delete.md was removed from the vault.
2026-06-22 | node scripts/sps-surfaces-smoke.mjs | PASS | 11/11 behavior screenshots passed after adding docs page-menu coverage: create subpage, rename, move to trash, restore, then existing dashboard/work/automation/insights/health checks.
2026-06-22 | node scripts/sps-surfaces-smoke.mjs | FAIL then fixed | Expanded right-panel smoke initially used an ambiguous Show outline text selector and then expected a seeded backlink that the runtime did not index; harness now scopes palette item clicks, closes palette overlays, and asserts actual Backlinks/Info empty states.
2026-06-22 | node scripts/sps-surfaces-smoke.mjs | PASS | 12/12 behavior screenshots passed: includes command-palette Show outline action, right-panel Outline/Notes/Backlinks/Info tabs, comment reply/archive/restore, plus prior dashboard/work/automation/health checks.
2026-06-22 | node scripts/sps-surfaces-smoke.mjs | FAIL | Plain non-debug Playwright Electron launch failed before app startup with Process failed to launch. DEBUG=pw:browser* runs launch and completes; tracked as harness launch flake, not a product behavior failure.
2026-06-22 | npx vitest run tests/db-pool.test.ts | PASS | 7 tests passed after fixing fresh writable DB initialization and skipping the messages_metadata cleanup trigger when the base messages table is absent.
2026-06-22 | npx eslint scripts/sps-surfaces-smoke.mjs src/main/db.ts tests/db-pool.test.ts | PASS | No lint output after adding doc persistence smoke coverage and the metadata-trigger regression tests.
2026-06-22 | npm run build | PASS | typecheck:node and typecheck:web passed; MCP bundles and Electron/Vite build completed after the metadata-trigger fix.
2026-06-22 | DEBUG=pw:browser* node scripts/sps-surfaces-smoke.mjs | PASS | 13/13 behavior screenshots passed: added document title/body persistence with markdown assertion; debug log showed no messages_metadata trigger error after the DB fix.
2026-06-22 | DEBUG=pw:browser* node scripts/sps-surfaces-smoke.mjs | PASS | 14/14 behavior screenshots passed after adding Journal coverage: create entry, edit title/body, return to timeline, set mood, reopen entry, and verify journal markdown frontmatter/body.